## Slide 1: Industry system
POD Migration plan

## Slide 2: POD migration plan
# | Step | Description | Estimation(6 devs team)
0 | Environment setup |  | 2 sprints
1 | Cross platform MVP1 layers | DBs, secrets manager, configuration changes, slack, Parameter store(optional) | ~3 sprints(must haves) or 4 sprints(optinals)
2 | Migrate from PROD shared account to Separate NP | serverless, jenkins, sns, s3, refactor CF components, cloudfront | ~4 sprints
3 | Access management implementation | configure, user info migration, code changes, user and entitlement migration, new sceens | ~3 sprints
Steps

## Slide 3: POD migration plan
Steps
# | Step | Description | Estimation(6 devs team)
4 | Synchronize new features | Merge changes, apply step 1-2 to new repos, run updated scripts | ~3 sprints
5 | Source code migration | Independent jenkins, GitHub, NPM | ~2 sprints
6.1 | DBs migration to PROD |  | 2 sprints
6.2 | Users migration to PROD |  | 
6.3 | Application deployment to PROD |  | 
7 | Shared account app shut down |  | 1 sprint
 | TOTAL |  | 20 sprint