## Slide 1: Value Capture Transformation
Prepared by Slalom for Bayer Crop Science
March 2019

## Slide 2
Our Understanding
Bayer is looking for a partner to help create a highly secure independent AWS environment to migrate their existing Value Capture platform to support additional external customers. As part of this effort, this team would:
  Work with existing Bayer ISO and Cloud Engineering teams to migrate the platform to a new environment
  Complete the framework for migration in ~6 months
  Design AWS Landing Zone and associated technologies for the migration effort
Notes:     Define Future State End to End Experience
    Identify and document a future state experience, including capabilities that are needed to enable the desired experience
    Identify Current State Capability Maturity
    Evaluate current state plan for the digital experience in support of the September launch of OTT products
    Identify opportunities to differentiate
    Based on competition and digital experience best practices, identify features that will differentiate the digital experience for OTT products

## Slide 3
Approach & Deliverables
Collaborative approach across 24 weeks in order to best design and build a company agnostic, secure, and independent AWS environment for the Value Capture Transformation. Slalom will work within an agile framework with the VCT development team for the project.
App Container/ Serverless Epic:
  Create proof of concept migration strategy for CloudFoundry & AWS Lambdas to ECS with Fargate
  Analysis of CI/CD tooling to integrate with ECS/Fargate
Database Services & Compliance Epic:
  Develop and operationalize a strategy to move databases into net new AWS account
    Potential solutions - Snapshots, VCP Peering, Postgres dump/restore
  Supplier will review current processes and analyze for SOX compliance
Messaging Platform Epic:
  Perform analysis and make recommendations for refactoring from current Kafka instance to one or multiple of the following technologies:
    AWS MKS
    Confluent Kafka as a Service
    AWS Kinesis
    Dedicated Kafka Instance
API Management Epic:
  Evaluate, plan and design move from Bayer’s Akana/Ocelot to independent instances
  Evaluate API Gateway and Ping integration
  Setup proof of concept of NGINX+
Secrets Management Epic:
  Conduct discovery and analysis on current Vault implementation and make recommendations for replacing Jumpbox and Secrets storage
  Integration testing with AWS Secret Manager to ensure rotation of keys between VCT and POD platforms
  Build test environment to support jumpbox and rotation of keys
Identity and Access Management Epic:
  Develop tool migration plan from Bayer Ping to a “cost per use” based solution that supports OAuth2 and SAML such as AWS Cognito
  Develop requirements matrix for SOX compliance
  Design RBAC and group authentication policies/controls
Monitoring & Logging Epic:
  Perform analysis and make recommendations for logging and monitoring
  Management analysis between maintaining an ELK stack and using Splunk Cloud
  Design baseline dashboards in ELK or Splunk
  Configure CloudWatch Alerts and centralized logging
DevOps Tools Epic:
  Build and deploy new instances of Jira and GitHub Enterprise
  Setup and configure database instances
Notes:     Define Future State End to End Experience
    Identify and document a future state experience, including capabilities that are needed to enable the desired experience
    Identify Current State Capability Maturity
    Evaluate current state plan for the digital experience in support of the September launch of OTT products
    Identify opportunities to differentiate
    Based on competition and digital experience best practices, identify features that will differentiate the digital experience for OTT products

## Slide 4
High Level Engagement Timeline
S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9-12
API Management
Monitoring and Logging
Discovery / Sprint 0
Design & Implementation
Kickoff
App Container Migration
AWS Account Creation / Landing Zone
Database Services
Weekly check in with sponsor
Estimated Fees: $812K for 24 weeks
Production Migration
Messaging Platform
Access Management
DevOps Tools
Monthly check in with ISO
PETCO Review

## Slide 5
Core Team
Slalom + VCT Team Structure & Responsibilities
Program / Project Management
VCT Team
Integrated Team
Legend:
Slalom Team
Full Stack Developers (6)
Cloud Architect (1)
Cloud Engineers (3)
Subject Mater Experts (as needed)
Solution Owner
Program Owner
Sponsor: George Mitchom
Client Leadership Team: Chris Carl, Joe Price, Brian Small, Nick Diaz
Extended Team
PETCO, ISO, Cloud Engineering
Role: complete project stories / task to ensure user stories and requirements are completed
Estimated commitment: 40 hours per week (100% of time)
Role: provide executive leadership to oversee project. Provide senior leadership to support project execution
Estimated commitment: 2-4 hours per week (<5% of time)
Role: oversee projects and manage Core Team.
Estimated commitment: 20 hours per week (close to 50% of time)
Role: provide guidance and expertise to support project from adjacent departments / capabilities
Estimated commitment: 1-2 hours per week (~5% of time)